## #LN00011
counter | Name | Project name | Issue key | Priority | priority_number | case_title | Status | Custom field | Sprint | Due Date | SYS_FISCAL_WEEK | Created | a | Project_size | Custom field | Custom field (Request Item) | Custom field (Request | notes | Objective | rowid
[8 empty] | (Progress) | [6 empty] | (Report/Table) |  | Owner)
0 | Orlando de la Peña | Merch SC Development | MSD-100 | Medium |  | Instock Trend Brief | To Do |  | MSD Agile 13 30/07/2021 | 2021-07-29 | 48 | 2021-07-15 |  |  |  | New Report - WebFOCUS |  |  | 0 | 1
0 | Jose Luis Silva | Merch SC Development | MSD-39 | Medium |  | New Report - Service level exceptions | BLOCKED |  |  | . | . | 2021-02-25 |  | Medium |  |  |  |  | 0 | 2
0 | Jose Luis Silva | Merch SC Development | MSD-53 | Medium |  | Create In-stock trend Summary | Documentation | 90% |  | . | . | 2021-04-08 |  |  |  | New Report - WebFOCUS |  |  | 0 | 3
0 | Orlando de la Peña | Merch SC Development | MSD-56 | Medium |  | Create In-stock trend charts | Documentation | 100% |  | . | . | 2021-04-08 |  |  |  | New Report - WebFOCUS |  |  | 0 | 4
1 | Orlando de la Peña | Merch SC Development | MSD-56/MSD-74 | Low |  | USA map Chart | To Do | 60% |  | . | . | 2021-05-25 | [6 empty] | 0 | 5
0 | Orlando de la Peña | Merch SC Development | MSD-61 | Medium |  | In-stock Trend All reports | Development |  |  | . | . | 2021-04-22 | [6 empty] | 0 | 6
1 | Orlando de la Peña | Merch SC Development | MSD-61/MSD-76 | Medium |  | DC Report | Documentation | 100% |  | 2021-07-02 | 44 | 2021-06-03 | [6 empty] | 0 | 7
0 | Jose Luis Silva | Merch SC Development | MSD-88 | Medium |  | In-Stock Trend by Item type | QA |  | MSD Agile 13 30/07/2021 | 2021-07-29 | 48 | 2021-07-01 | [6 empty] | 0 | 8
0 | Orlando de la Peña | Merch SC Development | MSD-89 | Medium |  | In-Stock Trend by Store type | Development | 80% | MSD Agile 13 30/07/2021 | 2021-07-29 | 48 | 2021-07-01 | [6 empty] | 0 | 9
1 | Orlando de la Peña | Merch SC Development | MSD-89/MSD-90 | High |  | In-Stock Trend by Store type Analysis | Code Review | 90% | MSD Agile 13 30/07/2021 | . | . | 2021-07-01 | [6 empty] | 0 | 10
1 | Orlando de la Peña | Merch SC Development | MSD-89/MSD-99 | Medium |  | In-Stock Trend by Store type Graph and Tables Design (add tabs) | Development | 40% | MSD Agile 13 30/07/2021 | 2021-07-29 | 48 | 2021-07-15 | [6 empty] | 0 | 11
0 | Jose Luis Silva | Merch SC Development | MSD-96 | Medium |  | Link In-Stock Trend reports | Analyzing |  | MSD Agile 13 30/07/2021 | 2021-07-29 | 48 | 2021-07-15 | [6 empty] | 0 | 12
1 | Jose Luis Silva | Merch SC Development | MSD-96/MSD-98 | Medium |  | In-Stock Trend report linking Development | Development |  | MSD Agile 13 30/07/2021 | 2021-07-29 | 48 | 2021-07-15 | [6 empty] | 0 | 13
0 | Juan Ramirez | Merch SC Support | MSS-1 | Medium |  | Create Table Relationship file | Backlog |  |  | . | . | 2020-06-19 |  | Medium | All | Other | Octavio Martinez |  | 0 | 14
0 | Juan Ramirez | Merch SC Development | MSD-21 | High |  | FY21 Objective - Process Improvement - Project - Create 2 new reports / enhancements | To Do |  |  | 2021-08-28 | 52 | 2021-01-21 |  |  |  | New Report - WebFOCUS | Octavio Martinez |  | 1 | 15
0 | Octavio Martinez | Merch SC Support | MSS-6 | High |  | FY21 Objective - Drive Operation - Create a report that summarizes the team activity in the week | In Progress |  |  | 2021-08-28 | 52 | 2021-01-21 |  | Small |  | New Report - Other | Octavio Martinez |  | 1 | 16